TsunamiLab
Project Report
Alexander Binsmaier,
Ludwig Peuckert

---
Dynamic Rupture Project
- Current assumption:
  - Displacement in bathymetry at timestep zero
  - Tsunami wave initially is „like the displacement“
    This is an easy simplification to the actual origin of a tsunami

---
- Goal:
  - Tsunami is a consequence of a rupture
    => Create a wave by reading seismological data

---
Timeline
- CW 51:
  - Remove bugs! Done
  - Get data from Mr Percy Galvez Done
- CW 52:
  - Find a way to get the data to a format usable in the simulation Done (Creating a netCDF file using time, x and y as dimension and displacement as variable)
    Data needs to be written to a netCDF file
  - Implement a dynamic displacement reader Done
    (Working)

---
Timeline
- CW 1:
  - Adjust writer to write bathymetry time dependent Done
    One minor bug left
- CW 2:
  - Adjust the simulation to get possibility to change bathymetry per timestep Done (Working)
- CW 3:
  - Simulate Tohoku Scenario with this approach and highlight the most significant changes
    Ongoing.
    Changing the format of the seismological data, (nearly) done.
    As soon as possible: Run simulation on Cluster